## MTR Table 4.4 (PC21 Projects)
NOMINATED OUTPUTS DELIVERED BY PC21 CAPITAL PROJECTS AND PROGRAMMES OF WORK
A |  |  |  | B
Project Information |  |  |  | Project Outputs - Baseline
Project ID Reference | Project Name | PC21 Programme | BU Date (if appropriate) | PC21 Output Ref Code | Output Units | PC21 | [5 empty] | PC27 |  |  |  | LWWP Output (Y/N)
PI_Project_ID | PI_Project_Name | PI_PC21_Prog |  |  |  | 2021-22 | 2022-23 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31
1 | 2 | 3 | 5 | 6 | 7 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38
Water Treatment Works
JA331 | Dungonnell Treatability Improvements | 04a | 2021-12-23 | 7 | Nr | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
JA319 | Dorisland Treatability | 4 | 2023-03-21 | 7 | Nr | 0 | 1 | 0 | 0 | 0 | 0 |  |  |  |  | N
JN538 | Derg WTW MCPA PEO Undertakings | 4 | 2023-03-31 | 7 | Nr | 0 | 1 | 0 | 0 | 0 | 0 |  |  |  |  | N
JN562 | Derg Treatability Improvements | 04a | 2023-03-31 | 7 | Nr | 0 | 1 | 0 | 0 | 0 | 0 |  |  |  |  | N
JL814 | Carmoney Treatability Improvements | 04a | 2023-05-31 | 7 | Nr | 0 | 0 | 1 | 0 | 0 | 0 |  |  |  |  | N
JS328 | Drumaroad Treatability Improvements | 04a | 2023-09-29 | 7 | Nr | 0 | 0 | 1 | 0 | 0 | 0 |  |  |  |  | N
JA330 | Altnahinch Treatability Improvements | 04a | 2024-03-25 | 7 | Nr | 0 | 0 | 1 | 0 | 0 | 0 |  |  |  |  | N
JA341 | Ballinrees WTW, MCPA treatment investigations | 4 | 2025-01-10 | 7 | Nr | 0 | 0 | 0 | 1 | 0 | 0 |  |  |  |  | N
JN569 | Glenhordial Treatability Improvements | 04a | 2024-12-31 | 7 | Nr | 0 | 0 | 0 | 1 | 0 | 0 |  |  |  |  | N
JN568 | Lough Fea Treatability Improvements | 04a | 2024-12-31 | 7 | Nr | 0 | 0 | 0 | 1 | 0 | 0 |  |  |  |  | N
JF616 | Seagahan Treatability Improvements | 04a | 2025-03-31 | 7 | Nr | 0 | 0 | 0 | 1 | 0 | 0 |  |  |  |  | N
JN571 | Upgrade to Killyhevlin | 04a | 2026-02-27 | 7 | Nr | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  |  | N
JN571 | Killyhevlin DWW Tank | 04a | 2026-02-27 | 7 | Nr | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  |  | N
JN570 | Lough Bradan Treatability Improvements | 04a | 2027-03-17 | 7 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
JN483 | Glenhordial WTW Sludge Improvements | 04a | 2027-03-23 | 7 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
JP703 | Belleek Treatability Improvements | 04a | 2027-03-31 | 7 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
JN567 | Loughmacrory Treatability Improvements | 04a | 2027-03-25 | 7 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
JV903 | Carran Hill Treatability Improvements | 04a | 2027-01-22 | 7 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
JV902 | Fofanny Treatability Improvements | 04a | 2027-03-29 | 7 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
JF617 | Clay Lake Treatability Improvements | 04a | 2027-03-30 | 7 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
JI151 | NIW Alpha WTWs Treatability Improvements | 04a | 2027-01-01 | 7 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
JL815 | Caugh Hill Treatability Improvements | 04a | 2027-03-30 | 7 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
Trunk Mains
JL790 | Northern WRZ Resilience | 05b | 2022-01-25 | 6 | Nr | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
JR519 | Trunkmain - Whitespots B | 05a | 2022-10-21 | 6 | Nr | 0 | 1 | 0 | 0 | 0 | 0 |  |  |  |  | N
JL807 | Trunkmain - Crescent Link | 05c | 2023-05-09 | 6 | Nr | 0 | 0 | 1 | 0 | 0 | 0 |  |  |  |  | N
JP702 | Trunkmain - Killyhevlin Cavanacross B | 05a | 2024-02-15 | 6 | Nr | 0 | 0 | 1 | 0 | 0 | 0 |  |  |  |  | N
JI212 | Beltoy and Unagh Drought Alleviation Pumping Stations | 05a | 2024-03-27 | 6 | Nr | 0 | 0 | 1 | 0 | 0 | 0 |  |  |  |  | N
JN563 | Western Resource Zone - Resilience | 05b | 2025-04-04 | 6 | Nr | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  |  | N
JG091 | Castor Bay Outage September 2019 | 05b | 2027-03-30 | 6 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
JL808 | Trunkmain - Skeoge Link | 05c | 2027-03-30 | 6 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
JG087 | Castor Bay to Ballydougan Trunk Main September 2019 | 05a | 2027-03-30 | 6 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
JN565 | Blacklough to Crocknabohill SR | 05a | 2027-03-30 | 6 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
JB739 | Central WRZ Resilience and Supply | 05b | 2027-03-05 | 6 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
JL715 | Caugh Hill, Carmoney to Strabane Strategic Link Watermain | 05a | 2027-03-30 | 6 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
JN573 | Edenasop to Killeter SR | 05a | 2027-03-24 | 6 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
JN572 | Woodend to Drain main | 05a | TBC | 6 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
JB743 | Trunkmain - High Tober | 05a | TBC | 6 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
JV904 | Aughnagun Drought Alleviation Pumping Station | 05a | 2026-03-30 | 6 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
JB746 | Craigpark SR Inlet | 05a | 2026-04-22 | 6 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
Service Reservoirs & Clear Water Tanks
JS274 | Drumaroad WTW Clear Water Tank | 06z | 2021-06-17 | 8 | Nr | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
JS308 | CWT - Fofanny | 06z | 2023-10-05 | 8 | Nr | 0 | 0 | 1 | 0 | 0 | 0 |  |  |  |  | N
JF615 | CWT - Seagahan | 06z | 2024-03-06 | 8 | Nr | 0 | 0 | 1 | 0 | 0 | 0 |  |  |  |  | N
JN564 | SR - Loughmacrory Hill | 06z | TBC | 8 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
JN576 | Loughmacrory Hill CWT PS | 06z | 2027-03-29 | 8 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
Unsatisfactory Intermittent Discharges
KR667 | Kircubbin DA Cooks Cove WwPS | 12b | 2021-10-28 | 12 | Nr | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
KS874 | Bangor DAP Works Package 3 - Belfast Lough UIDs | 12b | 2023-03-13 | 12 | Nr | 2 | 1 | 0 | 0 | 0 | 0 |  |  |  |  | N
KN688 | Cookstown DA - Derryloran Industrial Estate One WwPS | 12b | 2023-04-12 | 12 | Nr | 0 | 0 | 1 | 0 | 0 | 0 |  |  |  |  | N
KB562 | Carrick DA - Solution 3 - Irish Quarter South CSO | 12b | 2023-12-01 | 12 | Nr | 0 | 0 | 1 | 0 | 0 | 0 |  |  |  |  | Y
KB562 | Carrickfergus Rodgers Quay WwPS | 12b | 2023-12-01 | 12 | Nr | 0 | 0 | 1 | 0 | 0 | 0 |  |  |  |  | Y
KH009 | Portaferry DAP - Portaferry No 1 PS (North) | 12b | 2024-02-12 | 12 | Nr | 0 | 0 | 1 | 0 | 0 | 0 |  |  |  |  | N
KA298 | Blackcave DA - Solution 1 - Ballygalley Coast Road CSO | 12b | 2025-02-13 | 12 | Nr | 0 | 0 | 0 | 1 | 0 | 0 |  |  |  |  | N
KA298 | Blackcave DA - Solution 1 - Ballygalley Slipway WwPS CSO | 12b | 2025-02-13 | 12 | Nr | 0 | 0 | 0 | 1 | 0 | 0 |  |  |  |  | N
KL543 | Limavady DA - Bovally WwPS | 12b | 2024-04-29 | 12 | Nr | 0 | 0 | 0 | 1 | 0 | 0 |  |  |  |  | N
KL543 | Limavady DA UID-Ballyclose Street CSO | 12b | 2024-04-29 | 12 | Nr | 0 | 0 | 0 | 1 | 0 | 0 |  |  |  |  | N
KC493 | North Coast DA Ballycairn CSO CAI Playing Fields KC467 | 12b | 2024-07-31 | 12 | Nr | 0 | 0 | 0 | 1 | 0 | 0 |  |  |  |  | N
KR780 | Belfast DA- Dunlambert Park CSO | 12b | 2024-06-10 | 12 | Nr | 0 | 0 | 0 | 1 | 0 | 0 |  |  |  |  | Y
KB562 | Carrick DA - Solution 2 - Marine Highway Carpark Offline Storage | 12b | 2025-03-25 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Y
KB562 | Minorca Place CSO | 12b | 2025-03-03 | 12 | Nr | 0 | 0 | 0 | 1 | 0 | 0 |  |  |  |  | Y
KB562 | Market Place CSO | 12b | 2025-03-25 | 12 | Nr | 0 | 0 | 0 | 1 | 0 | 0 |  |  |  |  | Y
KB562 | Antrim Street Carrick CSO | 12b | 2025-03-25 | 12 | Nr | 0 | 0 | 0 | 1 | 0 | 0 |  |  |  |  | Y
KB562 | Taylors Avenue CSO | 12b | 2025-03-03 | 12 | Nr | 0 | 0 | 0 | 1 | 0 | 0 |  |  |  |  | Y
KB562 | Carrick DA - Marine Highway CSO Screen | 12b | 2025-03-03 | 12 | Nr | 0 | 0 | 0 | 1 | 0 | 0 |  |  |  |  | Y
KL480 | Culmore DA - Faughan Crescent WwPS | 12b | 2025-09-25 | 12 | Nr | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  |  | N
KR785 | Newtownbreda DA- Option B Knockbreckan CSO | 12b | 2025-08-20 | 12 | Nr | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  |  | N
KG183 | Portadown Drainage Area Network Improvements - Meadow Lane and Bann Street | 12b | 2025-10-17 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
KG183 | Meadow Lane One CSO | 12b | 2025-10-17 | 12 | Nr | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  |  | N
KG183 | Meadow Lane Two CSO | 12b | 2025-10-17 | 12 | Nr | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  |  | N
KG183 | Portmore Street CSO | 12b | 2025-10-17 | 12 | Nr | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  |  | N
KG183 | Clonavon Avenue CSO | 12b | 2025-10-17 | 12 | Nr | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  |  | N
KG183 | Meadow Lane Health Centre CSO | 12b | 2025-10-17 | 12 | Nr | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  |  | N
KG183 | Meadow Lane WwPS | 12b | 2025-10-17 | 12 | Nr | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  |  | N
KA263 | Dunadry WWPS Upgrade | 12 | 2025-06-27 | 12 | Nr | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  |  | N
KS903 | Annalong DAP | 12 | 2025-09-02 | 12 | Nr | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  |  | N
KS999 | Ballyrickard DA Upper Crescent Comber WwPS | 12b | 2025-05-17 | 12 | Nr | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  |  | N
KH011 | Downpatrick DAP - Down Council Strangford Road CSO | 12b | 2025-12-11 | 12 | Nr | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  |  | N
KA300 | Antrim DA Glenavy Road Crumlin WwPS | 12b | 2026-11-27 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KB564 | Ballymena DA - Dunfane Crescent | 12b | 2026-04-30 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KB564 | Ballymena DA - Harryville Bridge CSO | 12b | 2026-04-30 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KB564 | Ballymena DAP - N100010347 | 12b | 2026-04-30 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KH010 | Ballynahinch DA - Loughside Drive WwPS | 12b | 2027-03-30 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KH010 | Ballynahinch DA UID-Town CSO | 12b | 2027-03-30 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KN688 | Cookstown DA - Burn Bank CSO | 12b | 2027-03-30 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KN687 | Cookstown DA - Castle Road CSO | 12b | 2027-03-30 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KN688 | Cookstown DA - Coolreaghs Road CSO | 12b | 2027-03-30 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KN687 | Cookstown DA - Loran Way CSO | 12b | 2027-03-30 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KN687 | Cookstown DA - Orritor Road CSO | 12b | 2027-03-30 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KN687 | Cookstown DA - Unipork Molesworth Street CSO | 12b | 2027-03-30 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KT442 | Dromore DAP- Dromore Central PS10 WwPS | 12b | 2027-03-30 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KT442 | Dromore DAP- Dromore Central WwPS | 12b | 2027-03-30 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KT442 | Dromore DAP- Invert Siphon CSO | 12b | 2027-03-30 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KT442 | Dromore DAP- Lower Mount CSO | 12b | 2027-03-30 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KT442 | Dromore DAP- PS14 at Invert Siphon Site | 12b | 2027-03-30 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KH016 | Kilkeel DA - Derryogue Park CSO | 12b | 2027-03-31 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KH016 | Kilkeel DA - Military Rd WWPS, Corick Way and Kittys Rd CSO | 12b | 2027-03-31 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
KH016 | Military Road WwPS | 12b | 2027-03-31 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KH016 | Corick Way Kilkeel CSO | 12b | 2027-03-31 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KH016 | Kittys Road Two CSO | 12b | 2027-03-31 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KS991 | Kilkeel DA - Rooney Road CSO Uncharted | 12b | 2027-03-31 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KH008 | Killinchy DA - Inisharoan PS | 12b | 2027-01-04 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KL572 | Magherafelt DAP - Hospital Road East WwPS (ballyheafer) | 12b | 2027-02-26 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KL572 | Magherafelt DAP Mill View PS | 12b | 2027-02-26 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KR737 | Newtownbreda DA - Option B - Mill Road West CSO | 12b | 2026-11-27 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KC492 | North Coast DA Strand Road WwPS | 12b | 2026-09-30 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
KC492 | Waterside WwPS | 12b | 2026-09-30 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KC492 | Strand Road WwPS | 12b | 2026-09-30 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KS872 | Bangor DAP Work Package 1: Carnalea Stream UID | 12b | 2026-04-10 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KS902 | Dundrum DAP, UIDs Upgrades. | 12b | 2027-03-30 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
KS902 | Main Street Dundrum Three CSO | 12b | 2027-03-30 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KS902 | Flynns WwPS | 12b | 2027-03-30 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KS902 | Main Street Dundrum Two CSO | 12b | 2027-03-30 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
SP026 | Belfast DA Upper Falls Boucher CSO DO45 | 12b | 2027-03-31 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | Y
KR734 | Kinnegar DA- Brooklands Ave No.21 Sewerage | 12b | 2026-11-27 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | Y
KR734 | Kinnegar DA- Brooklands Crescent WwPS | 12b | 2026-11-27 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | Y
KR734 | Kinnegar DA- Comber Road Sewerage | 12b | 2026-11-27 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | Y
KR734 | Kinnegar DA- Comber Road WwPS | 12b | 2026-11-27 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | Y
KR734 | Kinnegar DA- Cumberland Road Sewerage | 12b | 2026-11-27 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | Y
KR734 | Kinnegar DA- Grand Prix Park Sewerage | 12b | 2026-11-27 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | Y
KR734 | Kinnegar DA- Millars Lane SPS Sewerage | 12b | 2026-11-27 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | Y
KR734 | Kinnegar DA- Moat Park/ Upper Newtonards Road Sewerage | 12b | 2026-11-27 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | Y
KR632 | Sydenham WwPS | 12b | 2028-12-27 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 |  |  | Y
KR747 | Lower Woodburn WwPS | 12b | 2024-06-27 | 12 | Nr | 0 | 0 | 0 | 1 | 0 | 0 |  |  |  |  | Y
KR761 | LWWP Greenisland Catchment CSOs | 12b | 2025-01-31 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Y
KR761 | Greenisland Four WwPS | 12b | 2023-11-30 | 12 | Nr | 0 | 0 | 1 | 0 | 0 | 0 |  |  |  |  | Y
KR761 | Greenisland Three WwPS | 12b | 2024-03-29 | 12 | Nr | 0 | 0 | 1 | 0 | 0 | 0 |  |  |  |  | Y
KR761 | Greenisland Two WwPS | 12b | 2024-09-30 | 12 | Nr | 0 | 0 | 0 | 1 | 0 | 0 |  |  |  |  | Y
KR761 | Old Shore Road CSO | 12b | 2025-01-31 | 12 | Nr | 0 | 0 | 0 | 1 | 0 | 0 |  |  |  |  | Y
KR763 | LWWP Seahill Catchment CSOs | 12b | 2027-03-31 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Y
KR763 | Ballyrobert Road CSO | 12b | 2023-09-08 | 12 | Nr | 0 | 0 | 1 | 0 | 0 | 0 |  |  |  |  | Y
KR763 | Ben Vista Holywood WwPS | 12b | 2023-12-04 | 12 | Nr | 0 | 0 | 1 | 0 | 0 | 0 |  |  |  |  | Y
KR763 | Old Quay Court WwPS | 12b | 2023-12-04 | 12 | Nr | 0 | 0 | 1 | 0 | 0 | 0 |  |  |  |  | Y
KR763 | Cultra Avenue CSO | 12b | 2024-02-13 | 12 | Nr | 0 | 0 | 1 | 0 | 0 | 0 |  |  |  |  | Y
KR763 | Craigavad WwPS | 12b | 2024-06-28 | 12 | Nr | 0 | 0 | 0 | 1 | 0 | 0 |  |  |  |  | Y
KR763 | Clanbrassil WwPS | 12b | 2024-10-18 | 12 | Nr | 0 | 0 | 0 | 1 | 0 | 0 |  |  |  |  | Y
KR763 | Main Street Old Mill Close CSO | 12b | 2024-10-18 | 12 | Nr | 0 | 0 | 0 | 1 | 0 | 0 |  |  |  |  | Y
KR763 | Glencraig WwPS | 12b | 2025-03-28 | 12 | Nr | 0 | 0 | 0 | 1 | 0 | 0 |  |  |  |  | Y
TBC | Aghacommon | 12b | 2027-03-31 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
TBC | Templepatrick 2 WwPS | 12b | 2027-03-31 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
TBC | Umry Lodge CSO | 12b | 2027-03-31 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KA263 | UID390 Dunadry WWPS Upgrade *this was double counted in table | 12 | 2025-04-29 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
KS873 | Bangor DAP Work Package 2: Rathmore Stream UIDs | 12 | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
KV249 | Annsborough DA UID-Mill Hill Castlewellan WwPS | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
KF428 | Armagh DA - Storm Tanks | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
KB555 | Ballymena DAP - Deramore Park CSO | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
KB563 | Ballymena DAP - Knockan Road CSO | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
KB559 | Ballymena DAP - Spencetown TPS | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
KB563 | Ballymena DAP - The Pentagon CSO | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
KB563 | Ballymena DAP - Waveney Road Yard CSO | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
KB563 | Ballymena DAP- Albert Place CSO | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
KR753 | Ballywalter DA UID-Ballywalter Fowler 1 CSO | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
KA298 | Blackcave DA - Solution 2 - Blackarch East CSO | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
KN688 | Cookstown DA - Blackhill CSO | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
KH011 | Downpatrick DAP - Ardenlee PS | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
KH011 | Downpatrick DAP - Ardfern PS | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
KH011 | Downpatrick DAP - Strangford Road PS | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
KF429 | Dungannon DA - Woodlawn Park CSO | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
KF429 | Dungannon DAP - Coolhill North WWPS | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
KP696 | Enniskillen DA - Derrychara Link CSO | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
KP696 | Enniskillen DA - Loughview Drive CSO | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
KP696 | Enniskillen DA - Rossory One WwPS | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
KP696 | Enniskillen DA-Riverview Enniskillen WwPS | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
KS991 | Kilkeel DA - Kilkeel WwTW Stormtanks | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
KC496 | Maghera DA UID-Largantogher Park CSO | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
KV248 | Newry DA Newpoint Greenbank TPS | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
KV248 | Newry DA Warrenpoint Rd Two WwPS | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
KS873 | North Down DA - KS873 Rathmore Stream UID | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
KG177 | Portadown DAP Annagh WwPS | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
SP026 | Belfast DA- Forfar Street CSO WwPS | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Y
SP026 | Belfast DA- Donegall Place Royal Avenue CSO Sewerage | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Y
SP026 | Belfast DA- Shore Road York CSO WwPS | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Y
SP026 | Belfast DA- North Howard Street CSO WwPS | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Y
SP026 | Belfast DA- Shankill Road Lanark CSO WwPS | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Y
SP026 | Belfast DA Oldpark Road CSO DO42 | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Y
SP029 | Kinnegar DA- Clara Way Sewage | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Y
SP029 | Kinnegar DA- Holywood Rd No.2 Sewerage | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Y
SP029 | Kinnegar DA- Knock Road | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Y
SP029 | Kinnegar DA- Knock Road Playing Fields Sewerage | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Y
SP029 | Kinnegar DA- Knocknagoney Country Park Sewerage | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Y
SP029 | Kinnegar DA- Orangefield Ave/ Sandhill Parade | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Y
SP029 | Kinnegar DA- Palmerston Rd/ Holywood Rd Sewerage | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Y
SP029 | Kinnegar DA- Parkway WwPS | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Y
SP029 | Kinnegar DA- Sandown Road No. 149 Sewerage | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Y
SP029 | Kinnegar DA - Glen Brae WwPS | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Y
SP027 | Carrick DA - Solution 1 - West Park WwPS | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Y
SP029 | Kinnegar DA- Abbey Park WwPS | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Y
SP029 | Kinnegar DA- Kensington Road WwPS | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Y
SP029 | Kinnegar DA- Knocknagoney Dale WwPS | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Y
SP029 | Kinnegar Da- Knocknagoney Drive WwPS | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Y
SP036 | Carrick DA - Solution 4 - WwTW Boundary CSO Storage Tank | 16a | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Y
SP036 | Carrick DA - Solution 4 - WwTW Storm Tanks Overflow | 16a | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Y
SP026 | Belfast DA - Ravenhill Road Ravensdene CSo WwPS | 12b | TBC | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Y
Wastewater Pumping Stations (Capacity Increase)
KR647 | Bangor DA Ballyrobert Bangor WwPS | 12c | 2021-09-22 | 12 | Nr | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
KL533 | Donnybrewer DA Eglinton Cottage Way WwPS | 12c | 2022-06-23 | 12 | Nr | 0 | 1 | 0 | 0 | 0 | 0 |  |  |  |  | N
KF378 | Tamnamore DA Clonmore Road Clontyclay WwPS | 12c | 2023-02-10 | 12 | Nr | 0 | 1 | 0 | 0 | 0 | 0 |  |  |  |  | N
KA270 | Antrim DA Neillsbrook WwPS | 12c | 2023-11-08 | 12 | Nr | 0 | 0 | 1 | 0 | 0 | 0 |  |  |  |  | N
KL542 | Ballymagorry DA Ballymagorry Tyrone WwPS | 12c | 2024-10-31 | 12 | Nr | 0 | 0 | 0 | 1 | 0 | 0 |  |  |  |  | N
KG140 | Moira DA Waringfield WwPS | 12c | 2025-01-30 | 12 | Nr | 0 | 0 | 0 | 1 | 0 | 0 |  |  |  |  | N
KG235 | Derryhale DA Dobbin WwPS | 12c | 2026-02-24 | 12 | Nr | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  |  | N
KV243 | Rathfriland Drumlough DA Sleepy Valley Rathfriland WwPS | 12c | 2025-09-26 | 12 | Nr | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  |  | N
KF426 | Derryhale DA - Brompton Park WwPS | 12c | 2026-05-22 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KS971 | Donaghadee DA - Cotton WWPS | 12c | 2026-10-23 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KF362 | Keady Armagh DA Annvale WwPS | 12c | 2026-12-17 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KF421 | Moy DA Keenaghan WwPS Upgrade | 12c | 2027-03-30 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
SP030 | New Growth LWWP | 12c | 2027-03-31 | 12 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Y
Wastewater Treatment Works
KL489 | Ballykelly WwTW | 16 | 2021-07-22 | 13 | Nr | 1 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
KV241 | Warrenpoint WwTW Phase 2 | 16a | 2022-11-15 | 13 | Nr | 0 | 1 | 0 | 0 | 0 | 0 |  |  |  |  | N
KS113 | Ards North, Carrowdore, Ballywalter, Ballyhaskin | 16 | 2023-01-18 | 13 | Nr | 0 | 3 | 0 | 0 | 0 | 0 |  |  |  |  | N
KS235 | Ballygowan WwTW | 16a | 2023-01-26 | 13 | Nr | 0 | 1 | 0 | 0 | 0 | 0 |  |  |  |  | N
KR730 | Loughries WwTW | 16a | 2023-02-16 | 13 | Nr | 0 | 1 | 0 | 0 | 0 | 0 |  |  |  |  | N
KB551 | Derrycrin WwTW | 16a | 2023-11-17 | 13 | Nr | 0 | 0 | 1 | 0 | 0 | 0 |  |  |  |  | N
KN681 | Pomeroy WwTW | 16a | 2024-03-15 | 13 | Nr | 0 | 0 | 1 | 0 | 0 | 0 |  |  |  |  | N
KN680 | Mountfield PC21 | 16a | 2024-03-22 | 13 | Nr | 0 | 0 | 1 | 0 | 0 | 0 |  |  |  |  | N
KB552 | Ballyronan WwTW | 16a | 2024-07-03 | 13 | Nr | 0 | 0 | 0 | 1 | 0 | 0 |  |  |  |  | N
KP704 | Tamlaght WwTW | 16a | 2024-09-03 | 13 | Nr | 0 | 0 | 0 | 1 | 0 | 0 |  |  |  |  | N
KL565 | Aghanloo WwTW | 16a | 2025-02-28 | 13 | Nr | 0 | 0 | 0 | 1 | 0 | 0 |  |  |  |  | N
KS981 | Newcastle WwTW | 16a | 2025-03-03 | 13 | Nr | 0 | 0 | 0 | 1 | 0 | 0 |  |  |  |  | N
KB556 | Grange (Taylorstown) WwTW | 16a | 2025-04-25 | 13 | Nr | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  |  | N
KP703 | Monea WwTW | 16a | 2025-07-30 | 13 | Nr | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  |  | N
KS996 | Drumaness WwTW | 16a | 2026-03-27 | 13 | Nr | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  |  | N
KP705 | Ballygawley WwTW | 16a | 2025-06-26 | 13 | Nr | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  |  | N
KN682 | Stewartstown WwTW | 16a | 2025-12-17 | 13 | Nr | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  |  | N
KH004 | Dundrum WWTW | 16a | 2025-07-10 | 13 | Nr | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  |  | N
KV245 | Meigh WwTW | 16a | 2026-03-31 | 13 | Nr | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  |  | N
KC494 | Kilrea WwTW | 16a | 2025-08-26 | 13 | Nr | 0 | 0 | 0 | 0 | 1 | 0 |  |  |  |  | N
KF423 | Cabragh WwTW | 16a | 2026-11-03 | 13 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KT439 | Dromore WwTW | 16a | 2026-08-21 | 13 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KF418 | Robinsonstown WwTW | 16a | 2026-12-08 | 13 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KF419 | Moy WwTW | 16a | 2027-03-08 | 13 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KB553 | Killygonlan WwTW | 16a | 2026-12-18 | 13 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KN683 | Cat 5- Lisnaskea 2 WwTW | 16a | 2027-03-26 | 13 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KN684 | Clogher WWTW | 16a | 2026-09-11 | 13 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KG234 | Waringstown WwTW | 16a | 2026-12-02 | 13 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KF425 | Dungannon WwTW | 16a | 2027-03-31 | 13 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KN685 | Lough Macrory WwTW | 16a | 2026-06-19 | 13 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KB554 | Bellaghy WwTW | 16a | 2026-12-16 | 13 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KR725 | Whitehouse WwTW | 16b | 2027-02-26 | 13 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | Y
KR726 | Belfast WwTW - Phase 1 upgrade | 16b | 2027-02-26 | 13 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | Y
KH002 | Annsborough WwTW | 16a | 2027-03-30 | 13 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KT443 | Dromara WwTW | 16a | 2027-03-30 | 13 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KF355 | Markethill WwTW | 16a | 2027-03-30 | 13 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KS998 | Downpatrick WwTW | 16a | 2027-03-30 | 13 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KS997 | Killinchy WwTW | 16a | 2027-03-30 | 13 | Nr | 0 | 0 | 0 | 0 | 0 | 1 |  |  |  |  | N
KV244 | Newry WwTW | 16a | 2030-11-07 | 13 | Nr | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | N
KR727 | Greenisland WwTW | 16b | 2030-02-06 | 13 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Y
KR728 | Carrickfergus WwTW | 16b | 2028-12-21 | 13 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | Y
KB558 | Larne WwTW | 16a | 2027-08-06 | 13 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
KL566 | Culmore WwTW- Cat 5 | 16a | 2029-12-28 | 13 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
KV252 | Kilkeel WwTW | 16a | TBC | 13 | Nr | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | N
Small Wastewater Treatment Works
SP038 | RWwIP RBC <50PE (Current PE) | 17z | 2027-03-30 | 14 | Nr | 2 | 10 | 4 | 7 | 7 | 6 |  |  |  |  | N
Small Wastewater Treatment Works (Sustainable Solutions)
SP038 | RWWIP – Sustainable Option | 17z | 2027-03-26 |  | Nr | 0 | 0 | 0 | 1 | 1 | 1 |  |  |  |  | N
Wastewater Siphons
KR623 | Belfast DA Queens Bridge Siphons | 12H | 2022-03-30 |  | Nr | 0 | 1 | 0 | 0 | 0 | 0 |  |  |  |  | Y
KL494 | Culmore DA Strathfoyle Siphons | 12i | 2024-12-31 |  | Nr | 0 | 0 | 0 | 1 | 0 | 0 |  |  |  |  | N
Event Duration Monitors
KI696/KI699/KI700 | Event Duration Monitors WwPS/CSOs | 12b | 2027-03-30 |  | Nr | 52 | 83 | 124 | 122 | 123 | 142 |  |  |  |  | N
KI835 | Event Duration Monitors WwTW | 16d | 2027-03-31 |  | Nr | 0 | 0 | 0 | 0 | 49 | 49 |  |  |  |  | N
BP T4.1 | Water Outputs |  |  |  |  | 2021-22 | 2022-23 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | PC21
19 | Completion of nominated trunk main schemes |  |  | 6 |  | 1 | 1 | 3 | 0 | 1 | 9 | 0 | 0 | 0 | 0 | 15
20 | Completion of nominated water treatment works schemes |  |  | 7 |  | 1 | 3 | 3 | 4 | 2 | 8 | 0 | 0 | 0 | 0 | 21
21 | Completion of nominated improvements to increase the capacity of service reservoirs and clear water tanks |  |  | 8 |  | 1 | 0 | 2 | 0 | 0 | 1 | 0 | 0 | 0 | 0 | 4
BP T4.2 | Sewerage Outputs |  |  |  |  | 2021-22 | 2022-23 | 2023-24 | 2024-25 | 2025-26 | 2026-27 | 2027-28 | 2028-29 | 2029-30 | 2030-31 | PC21
8 | Delivery of improvements to nominated UIDs as part of a defined programme of work |  |  | 12 |  | 4 | 3 | 11 | 20 | 14 | 48 | 0 | 1 | 0 | 0 | 100
9 | Delivery of improvements to nominated WwTWs as part of a defined programme of work |  |  | 13 |  | 1 | 6 | 3 | 4 | 8 | 18 | 0 | 0 | 0 | 1 | 40
10 | Small wastewater treatment works delivered as part of the rural wastewater investment programme |  |  | 14 |  | 2 | 10 | 4 | 7 | 7 | 6 | 0 | 0 | 0 | 0 | 36